REPUBLIC OF GHANA

BUDGET IMPLEMENTATION/ PERFORMANCE REPORT IN RESPECT

OF

SEKONDI TAKORADI METROPOLITAN ASSEMBLY

FOR THE PERIOD

JANUARY TO DECEMBER, 2024

SUBMITTED TO MINISTRY OF FINANCE

IN

ACCORDANCE WITH

Sections 27, 30 (3) & 34 (1 & 2) of the Public Financial Management Act, 2016, Act 921

Table of Contents

PART B: EXECUTIVE SUMMARY	5

Revenue Performance – All Source of Funds	5

POLICY OUTCOME INDICATORS AND TARGETS	7

POLICY OBJECTIVES IN LINE WITH SDGs, TARGETS AND COST FOR 2023	7

PART C: STRATEGIC OVERVIEW OF THE MMDA	12

VISION:	12

MISSION:	12

GOAL:	12

CORE FUNCTIONS:	12

DISTRICT ECONOMY	12

MONITORING AND EVALUATION MATRIX FOR PROGRAMME BASED BUDGET	15

30

PART D: KEY FINANCIAL PERFORMANCE BY PROGRAMME FOR THE PERIOD	32

PART E: SUMMARY OF EXPENDITURE BY ECONOMIC CLASSIFICATION	34

PART F: MMDAs CASH POSITION	35

PART G (i): SUMMARY OF 2022 IGF PERFORMANCE BY REVENUE ITEMS FOR THE PERIOD	36

(II): EXPENDITURES ON 2022 IGFS BY ECONOMIC CLASSIFICATION	36

PART H: STAFF ESTABLISHMENT BY GRADE (GOG ONLY)	37

PART I: IGF STAFF BY NON-ESTABLISHED POST	43

PART J: ACTIONS TAKEN TO IMPLEMENT THE RECOMMENDATIONS OF PARLIAMENT IN RESPECT OF THE MOST RECENT REPORT OF THE AUDITOR-GENERAL IN ACCORDANCE WITH SECTION 27(4)(d) OF PFM Act	44

PART K: DETAILS OF ON-GOING PROJECTS	45

PART L: CONCLUSION	50

PART A: PRINCIPAL ACCOUNT HOLDER’S (MMDCE) BRIEF

The Sekondi Takoradi Metropolitan Assembly for 2024 fiscal year performed creditably well in my view. The Composite Budget Statement for the 2024 fiscal year drew its authority from the Local Governance Act, 2016, (Act 936). Sekondi Takoradi Metropolitan Assembly’s budget, prepared using the Programme Based Budget approach by Medium Term Expenditure Framework (MTEF), was based on the 2024 Metropolitan Composite Action Plan.

This Programme based budget was categorized into five (5) budget programmes and fifteen (15) sub-programmes areas; Management and Administration, Social Service Delivery, Infrastructure Delivery & Management, Economic Development and Environmental and Sanitation Management.

An amount of GH₵ 21,577,048.99 was spent in respect of Management and Administration programme representing 85.57% of its allocation budget (GHS 25,215,884.00) whilst the amount formed 43.10% out of total expenditure (GH₵ 63,268,582.22) for the period.

The nominal performance of Social Service Delivery was 91.41% representing an amount of GH₵ 6,230,222.57 of its allocation budgets of GH₵ 6,815,634.00. The amount formed 9.85% of total expenditure made.

Nominal performance of 92.83% for Infrastructure Delivery and Management was realized representing an amount of GH₵ 12,689,289.23 of its allocation budgets of GH₵ 13,669,846.00. The amount formed 20.06% out of total expenditure made while 220.63% representing an amount of GH₵ 9,240,976.21 of its allocation budgets of GH₵ 4,188,400.00 was realized for Economic Development. This amount formed 14.61% of the total expenditure. An amount of GH₵ 13,531,045.22 representing 306.40% nominal budget performance of its allocation budget of GH₵ 4,416,160.70 for Environmental Management. This amount formed 21.39% of total annual expenditure.

At the close of 2024 fiscal year, an amount of GH₵ 63,268,582.22 had been spent out of an allocation for all budget programmes of GH₵ 76,563,193.16 representing 82.64%.

The department introduced the Budget Support Programme as a special initiative to partner philanthropic, donor, churches and well-meaning individuals within the metropolis support in cash or in kind the developmental agenda of the Assembly. In line with this the department has been able to engage 13 number of individuals and organizations to collaborate with the department for support to fund government projects.

Essipong, Diabene and Kojokrom have benefitted from the construction and completion of modern Reproductive Health Centers to increase health access in these communities. These were funded from European Union in partnership with STMA.

On a metro wide basis, the TSCPP funded the construction 100no. Bio-fill Household Toilet facilities. This was aimed at improving sanitation situation in the Metropolis and also reduce the prevalence of open defecation in the Metro.

Again, Ahanta Akromakrom and Kansaworodo have been handed 3-unit classroom block each to boost classroom access and facilitate a conducive teaching and learning environment. The District Road Improvement Programme (DRIP) has seen internal roads been giving some facelift.

Globally, climate change and its rippled effect on humanity is at the heart of governments and policy makers. The Paris agreement sought to bring together leaders of all nations to take on the challenge(s) of climate change. The Sekondi Takoradi Metropolitan Assembly has not either renege on her promise to take climate change.

In 2024, GIZ 	in collaboration with the Assembly completed the first phase of the Sustainable Energy Access Climate Action Plan (SEACAP) agreement.

Again, the implementation of the SYCA agreement which brough together Youth in Climate Action (SYCA) to showcase their knowledge and will to tackle climate related challenges in the Metropolis.

# PART B: EXECUTIVE SUMMARY

The tables below represent the Revenue and Expenditure Performance as at December, 2024

## Revenue Performance – All Source of Funds

|  | 2022 |  | 2023 |  | 2024 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| REVENUE HEAD | BUDGET | ACTUAL | BUDGET | ACTUAL | BUDGET | ACTUAL | % PERF |
| Retained IGF | 16,761,786.20 | 14,006,227.17 | 19,005,542.70 | 13,543,307.67 | 20,075,416.70 | 16,048,891.60 | 79.94 |
| GoG - Compensation | 11,718,041.27 | 17,649,295.75 | 11,694,511.00 | 23,912,951.69 | 25,800,806.46 | 30,820,933.33 | 119.46 |
| GoG – Goods / Services | 193,756.00 | 77,267.73 | 166,000.00 | 74,306.19 | 195,000.00 | - | - |
| DACF – Assembly | 5,891,829.73 | 2,615,884.16 | 6,547,829.73 | 1,809,180.23 | 4,030,704.00 | 4,023,411.12 | 99.82 |
| DACF- PWD | 440,000.00 | 299,935.03 | 200,000.00 | 141,300.03 | 200,000.00 | 252,998.09 | 126.50 |
| DACF – MP | 1,290,000.00 | 1,960,829.98 | 1,530,000.00 | 1,339,759.56 | 6,243,600.70 | 3,303,990.27 | 52.92 |
| DACF – RFG IG | 1,845,395.29 | 1,184,495.15 | 1,787,467.76 | 141,300.03 | 1,483,343.02 | 1,965,393.00 | 132.50 |
| DACF – RFG CG | 46,949.58 | 46,949.58 | 32,294.23 | - | 51,643.98 | - | - |
| Donor – UNICEF | 35,000.00 | 17,500.00 | 35,000.00 | 17,500.00 | 35,000.00 | 35,000.00 | 100.00 |
| Donor - EU | 8,281,732.86 | 5,413,288.00 | 12,866,432.00 | 13,151,907.00 | 16,347,680.00 | 5,596,390.00 | 34.23 |
| Donor-SYCA, SMART CITIES etc. | - | - | - | - | 2,100,000.00 | - | - |
| TOTAL | 46,504,490.93 | 42,971,737.52 | 53,665,077.42 | 53,990,212.37 | 76,563,194.86 | 62,047,007.41 | 81.04 |

From the table, it could be inferred that the Assembly generated an amount of GHc16,048,891.60 IGF representing a performance rate of 79.94% of the budgeted total IGF Revenue of GHc 20,075,416.70.

It is worth noting that there was 106.21% release of Central Government Transfers as at December, 2024. This is made up of GHc 40,366,725.81 actuals against a budgeted figure of GHc 38,005,098.16. Central government Transfers include GOG- Compensation, GOG- Goods and Services and DACF (Assembly, MP, RGF)

Total donor transfer from EU, UNICEF and SYCA amounted to GHc 5,631,390.00 from a projected figure of GHc 18,482,680.00 representing a 30.47 % performance.

Total actual revenue realised amounted to GHc 62,047,007.41 representing a performance of 81.04% of the overall budget figure of GHc 76,563,194.86

EXPENDITURE BY ECONOMIC CLASSIFICATION

| EXPENDITURE ITEM | APPROVED BUDGET (2024) | AMOUNT FOR THE PERIOD (2024) | ACTUAL EXPENDITURE (2024) | ACTUAL PAYMENTS (2024) | PROJECTIONS FOR NEXT Period (2025) |
| --- | --- | --- | --- | --- | --- |
| Compensation of Employees | 28,594,170.46 | 18,449,726.00 | 33,250,401.39 |  | 35,660,343.21 |
| Goods and Services | 36,975,129.38 | 28,829,500.00 | 26,000,533.80 |  | 33,675,344.45 |
| Capital Expenditure | 10,993,893.32 | 7,416,623.00 | 4,017,647.33 |  | 8,489,440.23 |
| Total | 76,563,193.16 | 54,695,849.00 | 63,268,582.52 |  | 77,825,127.89 |

The table above is a representation of the expenditure of the Assembly as at December, 2024. Comprising GHc 33,250,401.39 on Compensation of Employees, GHc 26,000,533.80 on Goods and Services and GHc 4,017,647.33 had been spent utilized on Assets.

The Assembly therefore achieved an overall performance utilization rate of 82.64% by consuming GHc 63,268,682.52 of the total budgets of GHc 76,563,193.16

## POLICY OUTCOME INDICATORS AND TARGETS

# POLICY OBJECTIVES IN LINE WITH SDGs, TARGETS AND COST FOR 2024

| FOCUS AREA | ADOPTED POLICY OBJECTIVES | GENERAL SDG GOAL | SPECIFIC SDG GAOL | BUDGET ALLOCATION |
| --- | --- | --- | --- | --- |
| Local Government and Decentralization. | Promote Social, economic, political inclusion. | Goal16: Peace, Justice and strong institution. | Develop effective, accountable and transparent institution at all levels. (SDG Target16.6) | 6,054,906.51 |
|  |  | Goal17: Strengthen the means of implementing and revitalizing the goal partnership for sustainable development. | Strengthen local level capacity for participatory planning & budgeting. (SDG Target16.7) |  |
|  |  |  | Strengthen Sub-District Structure. (SDG Target 15.6. 17.9). |  |
| Local Government and Decentralization. | Strengthen Domestic Revenue Mobilization. | Goal 17: Strengthen the means of implementing & revitalize the Goal partnership for sustainable Development. | Eliminating Revenue Collection leakage. (SDG 16.5. 16.6, 17.1) | 2,010,000.00 |
|  |  |  | Diversify Sources of Revenue Mobilization. (SDG Target 17.1, 17.3) |  |
| Education and Training. | Ensure free, equitable and quality education for all by 2030. | Goal 4: Inclusive and Equitable Quality Education. | Ensure infrastructure and Facility at all level (SDG Target 4.1) | 1,015,166.00 |
|  |  |  | Ensure Adequate Supply of Teaching and Learning Materials (SDG Target 4.c) |  |
| Health and Health Services. | Ensure affordable, equitable, easily accessible and Universal Health Coverage.(UHC) | Goal 3: Good Health and Wellbeing. | Expand and equip Health Facility (SDG Target3.8) | 1,556,096 |
|  |  |  | Accelerate implementation of (CHPS) policy to ensure equity in access to quality healthcare(SDG Target 201, 1.3, 3.1, 3.2, 3.3, 3.8, 16.6) |  |
| Agricultural and Rural Development. | Improve production efficiency and yield. | Goal 2: End Hunger, achieve food security and improved nutrition and promote sustainable agriculture. | Ensure effective implementation of the yield improvement program.(SDG Targets 2.1, 2.4) | 1,010,134 |
|  |  | Goal12: Ensure sustainable consumption and production patterns. | Reinvigorate Extension Services(SDG Target 2.a) |  |
| Social Protection. | Improvement appropriate Social Protection sys. & measures. | Goal 16: Promote peaceful and inclusive societies for sustainable development, provide access to justice for all and build effective, accountable and inclusive institution at all levels. | Strengthen and effectively implement existing social protection intervention programmes and expand vulnerable group (SDG Targets 1.3, 5.4, 10.4) | 1,145,462 |
| Environmental Management | Promote efficient and sustainable waste water management. Reduce environmental pollution. | Goal 6: Clean water and sanitation. | Improve Liquid Waste Management (SDG Target 6.3, 6.a, 6.b) | 5,703,751 |
|  |  | Goal 11: Sustainable cities and communities. | Provide mechanized boreholes and small-town water systems (SDG Target 6.1) |  |
|  |  |  | Improve Management of Waste disposal sites to control greenhouse gas emissions(GHGs) (SDG Target 11.6) |  |
| Disaster Management. | Promote proactive planning for disaster prevention and mitigation. | Goal 3: Good Health and Wellbeing. Goal 13: Climate Action. | Strengthen early warning and response mechanism for disasters(SDG Targets 3.d, 13.3) | 240,000.00 |
| Human Settlement, Works and Housing. | Enhance inclusive urbanization & capacity for settlement planning. | Goal 11: Sustainable cities and communities. | Fully implement Land use and spatial Planning Act,2016(Act 925) (SDG Targets 16.6, 17.16) | 6,249,011 |
|  |  | Goal 9: Build resilient infrastructure, Promote inclusive and sustainable development. | Develop quality reliable, sustainable and resilient infrastructure including Regional & Trans- Border. (SDG Target 9.1) |  |
| Private Sector Development. | Enhance business enabling environment. | Goal 9: Industry, innovation and infrastructure. | Implement One District, One Factory initiative(SDG Targets 9.2, 9.3, 9.4, 9.b, 9.c) | 130,000.00 |
| Roads and Transport | Improve transport and Road Safety |  |  | 18,688,576.28 |
| Water and Sanitation | Universal access to safe drinking water by 2030 |  |  | 250,000.00 |
| GRAND TOTAL |  |  |  | 42,520,864.79 |

KEY ISSUES / CHALLENGES IN THE MUNICIPALITY

- Inadequate engineered road networks linking some communities

- Poor Drainage System leading to flooding during heavy downpour in some communities

- Inadequate Educational and Health infrastructural facilities

- Inadequate Sanitation Infrastructure

- Non adherence to Sanitation Bye – Laws.

- Increasing Rate of Youth Unemployment

- Uncontrolled Sand Winning Activities

- Reducing Rate of Arable Land for Agriculture

- Haphazard Development

- Issues of Security Challenges

EFFORTS TO ADDRESS THE CHALLENGES

- Construction of Major Roads and Regular Reshaping of Unengineered Roads linking communities

- Construction and Expansion of Drains and Culverts to mitigate the incidents of Flooding in the Municipality

- Formation of Partnership with Hydro Dept. to assist in mitigating Flood.

- Construction & Rehabilitation of School Blocks and Health Centers to improve on facilities

- Construction of Refuse Bays and Provision of other Sanitary Facilities to control waste

- Regular Public Education on Proper Waste Disposal

- Promotion of LED Activities to minimize youth unemployment.

- Regular Development Control exercise to reduce unauthorized structures for better planned layout

- Regular MUSEC meetings to maintain Law and Order

KEY ACHIEVEMENTS IN 2022

- Valuation & Revaluation of Selected Properties (Residential and Commercial)

- Desilting of major Drains in the Municipality (Effia Storm drain, Anaji fie, Takoradi Technical Institute, I-Adu via Choice Mart, Koobi Bar to Total Filling Station)

- Constructed Culverts at Bulley Road and Apollo with side drains and approach filling

- Constructed Culverts to link Assakae – Adientem Road

- Constructed Culverts at Mexx Media with side Drains Road approach filling

- Constructed Storm Drain from Kojo Kumi Avenue – Kwesimintsim Goil Filling station (500m) with 1no. pedestrian crossing

- Completed construction of (1.6 KM) WAMCO – Effiakuma Road

- Distributed items to Twenty-One (21) People with Disability (PWD) beneficiaries made up of 7 Males and 14 Females for Economic Empowerment

- Distributed 12,000 Oil Palm Seedlings to 97 farmers, made up of 46 males and 51 females

- Distributed 5,000 Coconut Seedlings to 61 farmers, made up of 26 males and 35 females

- Completed construction of (1no.) CHPS Compound at Adientem (Phase 1)

- Organization of three (3) BECE Mock Exams in the Municipality

- Reconstructed 1 No. Open Market Shed and Drainage at Assakae Market (Phase 2)

- Completed construction of 1 No. 30 partitioned Market Bay at Whindo

- Completed construction of Foot Bridge at Kwesimintsim

- Completed magistrate court & Bungalow at Apollo& Whindo respectively

- Maintenance and replacement of street lights in the Municipality

# PART C: STRATEGIC OVERVIEW OF THE MMDA

## VISION:

To become a vibrant local democracy that promotes effective, transparent and proactive delivery of services’ as well as spatial infrastructure development.

## MISSION:

To mobilize all available resources and utilize them effectively and efficiently to facilitate improvement in the quality of life of the people through equitable provision of socio-economic services

## GOAL:

Improving the welfare and standard of living of the citizens as well as create excellent living conditions.

## CORE FUNCTIONS:

- Be responsible for the overall development of the district

- Formulate programs and strategies for the effective mobilization and utilization of human, physical, financial and other resources of the district.

- Promote and support productive activity and social development in the district and remove any obstacle to initiative and development.

- Initiate programs for the development of basic infrastructure and provide municipal works and service in the district

- Be responsible for the development improvement and management of human settlement and the environment in the district

- In co-operation with the appropriate national and local security, agencies are responsible for the maintenance of security and public safety in the district.

## DISTRICT ECONOMY

  - Health

The Municipality has 42 health facilities made up of both public and private facilities. These comprise six (6) hospitals, five (5) health centres, 15 clinics, two (2) maternity homes (2) and 14 functional CHPS Zones.

  - Education

There are 323 educational institutions (public and private) in the municipality comprising 87 kindergarten, 109 primary, 116 junior high, four (4) senior high schools, three (3) technical/vocational training school and four (4) tertiary institutions.

  - Agriculture

Agriculture, employs 6.2 percent of the economically active population are employed. The major crops cultivated in the Municipality can be put in four groups: cash crops (oil palm); cereals (maize), starchy staples/roots and tubers (cassava and plantain) and fruits and vegetables. Agriculture in the Municipality can best be described as urban agriculture which mainly takes place in the northern sector of the Municipality, namely Assakae, Mpatado and Whindo

The production of food and cash crops continues to be challenge with farmers having limited access to capital, high cost of production inputs, low application of technology (especially among smallholder farmers) leading to comparatively lower yields, poor storage facility ,  poor transportation systems, poor marketing systems, heavy post-harvest losses and inadequate extension officers to offer extension services to farmers.

  - Tourism

The Municipality is endowed with cultural and ecotourism assets that provides significant opportunity for tourism development and quality jobs creation. The Municipality can boast of the Kundum Festival, the Whin estuary as well as very good hotels and a modern shopping mall within its catchment area.

In the context of culture, the Kundum festival which is the main traditional festival celebrated annually by the various communities within the Municipality could be repackaged and promoted to attract tourists from within and outside Ghana to provide significant opportunities for jobs at all levels in the tourism value chain. Again the activities of the various Masquerade groups in the Municipality can be well packaged to attract tourists to EKMA in December of every year.

In terms of ecotourism potentials, the Municipality can boast of the Whin estuary, which is located around Apremdo and Apollo communities. It is populated by a lush mangrove vegetation, which serves as nursery for fishes and home for different species of flora and fauna. Currently there are two private tourist resorts operating in the area but potential exists for more and bigger resorts to be established around the beautiful estuary.

  - Energy

All the communities within the Municipality have electricity connectivity.  93.1 percent of households use electricity as their source of lighting for dwellings (PHC 2010). However, the communities, connected to the national grid, experience power surges.

The main issues with energy for lighting in the Municipality are: erratic power outages and the high cost of electricity to households and businesses.

The main sources of fuel for household cooking in the Municipality (PHC 2010) are as follows: Charcoal (48.9%), Gas (37.1%) and firewood (5.5%). The over-reliance on charcoal as the key source of fuel poses a great threat to the green environment, hence, the Assembly should come out with strategies to discourage people from using charcoal and instead promote the use of Liquidified Petroleum Gas (LPG) and other environmentally friendly source of energy including solar. Such intervention would go a long way to help protect the fragile ecosystem.

  - Banking and other Financial Services

There are three (3) main types of financial institutions that are operating in the municipality. These can conveniently be classified as commercial, rural banks and savings and loans institutions. The prominent Rural Banks operating in the Municipality are Lower Pra and Ahantaman Rural Banks. Fidelity Bank is the only major commercial bank operating office in the Municipality. However, other major Commercial Banks including Barclays, Stanbic, Cal Bank, Ecobank, Ghana Commercial Bank, Zenith Bank are operating indirectly in the Municipality via Automated Teller Machines (ATMs) positioned at vantage points such as Takoradi Technical University campus, Takoradi Mall and Anaji Choice Mart. The major Savings and Loans Institutions operating in the Municipality include GESRO, Dalex Finance, Bay Port, IZWE Loans among others.

## MONITORING AND EVALUATION MATRIX FOR PROGRAMME BASED BUDGET

| Management and Administration |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| National Objective: Promote good corporate governance |  |  |  |  |  |  |  |  |  |  |
| Programme Objective: To facilitate and coordinate activities of department of the Assembly |  |  |  |  |  |  |  |  |  |  |
| Sub-Programme | Type of Indicator | Description of Indicator | Unit of Measure of Indicator | Baseline (2021) Actuals |  | 2022 |  |  |  | Remarks |
|  |  |  |  |  |  | Budget Year Target 2022 |  | Annual Actual; | Variance |  |
| Sub Programme Objective: Strengthen policy formulation, planning and, Monitoring & Evaluation processes at all levels |  |  |  |  |  |  |  |  |  |  |
| General Administration | Outcome 1: Enhanced Administrative Management of the Assembly |  |  |  |  |  |  |  |  |  |
|  | Output 1.1 | Quarterly management meetings annually organized | Number of quarterly meetings held | 4 |  | 4 |  | 4 | 0 |  |
|  | Output 1.2 | Compliance with Procurement procedures met | Procurement Plan prepared and approved by 31st September | Procurement Plan prepared and approved on 27th October |  | Procurement Plan prepared and approved by 31st September |  | Procurement Plan prepared and approved on 31st September | - |  |
|  | Output 1.3 | Quarterly Internal Audit Report submitted to Audit Committee | Number of Audit assignments conducted with reports. | 4 |  | 4 |  | 4 | 0 |  |
| Sub Programme Objective:Ensure effective and efficient mobilization of resources and its utilization |  |  |  |  |  |  |  |  |  |  |
| Finance and Audit | Outcome 2: Ensure sound financial management of the Assembly |  |  |  |  |  |  |  |  |  |
|  | Output 2.1 | Financial reports prepared and Submitted | Monthly Financial Management Reports | 12 |  | 12 |  | 12 | 0 |  |
|  | Output 2.2 | Count of Quarterly Financial Management Reports submitted by 15th of the following month | 4 | 4 |  | 4 |  | 4 | 0 |  |
|  | Output 2.3 | Annual Statement of Accounts submitted by 15th of January | 2020 Annual Accounts prepared and Submitted on 15th of January | 2021 Annual Accounts prepared and Submitted by 15thof January |  | 2022 Annual Accounts prepared and Submitted on 15th of January |  | 2022 Annual Accounts prepared and Submitted on 15th of January | - |  |
|  | Output 2.4 | Quarterly Financial Management Reports submitted by 15th of the following month | 4 | 4 |  | 4 |  | 4 | 0 |  |
|  | Output 2.5 | Average annual growth of IGF by at least 10% achieved | Annual IGF percentage growth |  |  |  |  |  |  |  |
|  | Output 2.6 | Quarterly Audit Committees(AC) organized | Count of AC meetings held | 2 |  | 4 |  | 4 | 0 |  |
| Sub Programme Objective: Develop adequate skilled human resource base |  |  |  |  |  |  |  |  |  |  |
| Human Resource Management | Outcome 3: Develop adequate skilled human resource base |  |  |  |  |  |  |  |  |  |
|  | Output 3.1 | Staff appraised annually | Number of staff appraisal conducted | 120 |  | 134 |  | 124 | 10 |  |
|  | Output 3.2 | Human Resource Management Information System (HRMIS) updated | Number of updates and submissions to RCC | 12 |  | 12 |  | 12 | 0 |  |
|  | Output 3.3 | Capacity building plan prepared and implemented | Composite training plan approved by | 13th December |  | 31st December |  | 15th December |  |  |
|  |  |  | Number of training workshop held internally | 7 |  | 7 |  | 6 | 1 |  |
|  | Output 3.4 | Salary Administration | Monthly validation ESPV | 12 |  | 12 |  | 12 | 0 |  |
| Sub Programme Objective: Strengthen policy formulation, planning and, Monitoring & Evaluation processes at all level |  |  |  |  |  |  |  |  |  |  |
| Planning, Budgeting, Coordination and Statistics | Outcome 4: Strengthen policy formulation, planning and, Monitoring & Evaluation processes at all level |  |  |  |  |  |  |  |  |  |
|  | Output 4.1 | Annual Composite Action Plan Prepared | Annual Composite Plan Document prepared and approved by 30th September of the year subsequent to budget year | Action Plan prepared by 31st October |  | Action Plan prepared by 30th September |  | Action Plan prepared on 30th September |  |  |
|  | Output 4.2 | Annual Composite Budget Prepared and approved | Annual Composite Budget Document prepared and approved by 30th September of the year subsequent to budget year | Annual Composite Budget prepared and approved on 27th October |  | Annual Composite Budget prepared and approved by 30th September |  | Annual Composite Budget prepared and approved on 30th September |  |  |
|  | Output 4.3 | Fee Fixing Resolution Gazetted | Assembly’s fee fixing resolution Gazetted |  |  |  |  |  |  |  |
|  | Output 4.4 | Monitoring & Evaluation undertaken | Number of quarterly monitoring reports submitted | 4 |  | 4 |  | 4 | 0 |  |
|  |  |  | Annual Progress Report to be completed by March of ensuing year | 15th March |  | 15th March |  |  |  |  |
|  | Output 4.5 |  | Annual Progress Report(APR) to be completed by March of ensuing year | 2020 APR completed by 28th February, 2021 |  | 2021 APR completed by March, 2022 |  | 2021 APR completed on 25th February, 2022 |  |  |
|  | Output 4.6 | Social Accountability meetings held | Number of Town Hall meetings organized | 2 |  | 2 |  | 2 | - |  |
| Sub Programme Objective: To ensure full implementation of the political, administrative and fiscal decentralization reforms. |  |  |  |  |  |  |  |  |  |  |
| Legislative Oversights | Outcome 5: full implementation of the political, administrative and fiscal decentralization reforms ensured. |  |  |  |  |  |  |  |  |  |
|  | Output 5.1 | Decentralisation Process accelerated | Number of General Assembly Meetings Organised with minutes available |  | 4 | 4 | 3 |  | 1 |  |
|  |  |  | Number of Executive Committee Meetings Organised with minutes available |  | 3 | 4 | 3 |  | 1 |  |

| SOCIAL SERVICES DELIVERY |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| National Objective: Ensure free, equitable and quality education for all by 2030 |  |  |  |  |  |  |  |  |  |
| Programme Objective: Enhance inclusive & equitable access & participation in education at all levels |  |  |  |  |  |  |  |  |  |
| Sub-Programme | Type of Indicator | Description of Indicator | Unit of Measure of Indicator | Baseline (2021) Actuals | 2022 |  |  |  | Remarks |
|  |  |  |  |  | Budget Year Target 2022 |  | Annual Actual | Variance |  |
| Sub Programme Objective: Enhance inclusive & equitable access & participation in education at all levels |  |  |  |  |  |  |  |  |  |
| Education, Youth and Sports and Library services | Outcome 1: Enhance inclusive & equitable access & participation in education at all levels |  |  |  |  |  |  |  |  |
|  | Output 1.1 | Educational Planning and Supervision Improved | % of Management Staff trained | 80 |  | 85 | 82 |  |  |
|  |  |  | % of Schools monitored annually | 100 |  | 100 | 100 |  |  |
|  |  |  | % of Basic Schools monitored annually by DEOs and Circuit Supervisors | 100 |  | 100 | 100 |  |  |
|  | Output 1.2 | Increased Enrolment | Gross Enrolment Rate (GER) | 86 |  | 100 | 87 |  |  |
|  |  |  | Net Enrolment Rate (NER) | 71.8 |  | 90 | 72.45 |  |  |
|  |  |  | Gender Parity Index (GPI) | 1.1 |  | 1 | 1.1 |  |  |
|  | Output 1.3 | Increased/improved educational infrastructure and facilities | Number of classroom blocks constructed | 6 |  | 15 | 0 |  |  |
|  |  |  | Number of school furniture supplied 264 | 1 |  | 3 | 0 |  |  |
|  | Output 1.4 | Knowledge in science and math’s. and ICT in Basic and SHS improved | Number of participants in STMIE clinics | 60 |  | 60 | 48 |  |  |
|  | Output 1.5 | Improved performance in BECE | % of students with average pass mark | 69.71 |  | 85 | RESULT SHEET NOT YET IN |  |  |
| Sub Programme Objective: Ensure sustainable, equitable and easily accessible healthcare services |  |  |  |  |  |  |  |  |  |
| Public Health Services and Management | Outcome 2 : Sustainable, equitable and easily accessible healthcare services ensured |  |  |  |  |  |  |  |  |
|  | Output 2.1 | Immunization and roll back malaria programme annually organized | Number of infants immunized (Measles 2) | 7732 | 7115 |  | 5479 | 1636 |  |
|  |  |  | Number of households supplied with mosquito nets | 85,757 |  |  |  |  |  |
|  | Output 2.2 | Ensured sustainable, equitable and easily accessible healthcare services | Number of functional CHPS Zones established in deprived areas | 13 |  |  |  |  |  |
| Sub Programme Objective: Improve access to sanitation |  |  |  |  |  |  |  |  |  |
| Environmental Health and Sanitation Services | Outcome 3: Environmental Health and Sanitation Services |  |  |  |  |  |  |  |  |
|  | Output 3.1 | Improved environmental sanitation | Number of disposal site created and managed | 24 | 5 |  | 1 | 4 |  |
|  |  |  | Number food vendors tested and certified | # 1100 | # 1689 |  | 1314 | 375 |  |
|  |  |  | Number communities sensitized | 13 | 19 |  | 14 | 5 |  |
|  |  |  | Number of clean up exercise organized | 4 | 4 |  | 3 | 1 |  |
|  | Output 3.2 | Established sanitation courts | Number of individuals/house-holds prosecuted | 83 | 90 |  | - | 90 |  |
| Sub Programme Objective: Establish an effective and efficient social protection system |  |  |  |  |  |  |  |  |  |
| Social Welfare and Community Development | Outcome 4: Effective and efficient social protection system established |  |  |  |  |  |  |  |  |
|  | Output 4.1 | Increased assistance to PWDs annually | Number of beneficiaries | 43 | 30 |  | 21 | 9 |  |
|  | Output 4.2 | Social Protection programme (LEAP) improved annually | Number of beneficiaries | 71,768 | 71,768 |  | 71,768 | - |  |
|  | Output 4.3 | Capacity of stakeholders enhanced | Number of communities sensitized on self-help projects | 8 | 20 |  | 6 | 14 |  |
|  |  |  | Number of public educations on gov’t policies, programs and topical issues | 8 | 13 |  | 9 | 4 |  |
|  | Output 4.4 | Impact of the disability fund on the socio- economic development of the disabled assessed | Number of Disabled persons assisted | 54 | 30 |  | 26 | 4 |  |
|  |  |  | Income generating activities undertaken by persons with disability monitored | 38 | 30 |  | 19 | 11 |  |
|  | Output 4.5 | Community development undertaken | Number of communal labours supervised | 4 | 12 |  | 6 | 4 |  |
|  | Output 4.6 | Community education undertaken | Number of mass meetings conducted | 12 | 12 |  | 10 | 2 |  |
|  |  |  | Number of study groups educated | 10 | 15 |  | 12 | 3 |  |
|  | Output 4.7 | Citizenry sensitized on developmental issues | Community durbars organized on identification of needs of the communities |  |  |  |  |  |  |
| Social Welfare and Community Development | Output 4.8 | Promotion of child rights and protection enabled | Number of child welfare cases solved | 10 | 20 |  | 16 | 4 |  |
|  | Output 4.9 | Disbursement of LEAP Grant undertaken | Number of beneficiary households | 455 | 455 |  | 455 | - |  |
|  | Output 4.10 | Early childhood care and development enhanced | Number of pre-school/day care inspected | 15 | 50 |  | 34 | 16 |  |
|  | Output 4.11 | Self-help projects undertaken in communities | Workshops for local Artisans organized | 2 | 2 |  | 1 | 1 |  |
|  | Output 4.12 | Functionality of the sub-structures enhanced | All nine zonal councils functioning |  |  |  |  |  |  |

| INFRASTRUCTURE DELIVERY AND MANAGEMENT |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| National Objective: Facilitate sustainable and resilient infrastructure development |  |  |  |  |  |  |  |  |
| Programme Objective: To plan, manage and promote harmonious, sustainable and cost-effective development of human settlements in accordance with sound environmental and planning principles. |  |  |  |  |  |  |  |  |
| Sub-Programme | Type of Indicator | Description of Indicator | Unit of Measure of Indicator | Baseline (2021) Actuals | 2022 |  |  | Remarks |
|  |  |  |  |  | Budget Year Target | Annual Actual | Variance |  |
| Sub Programme Objective: Create & sustain an efficient and effective transport system |  |  |  |  |  |  |  |  |
| Roads and Transport Services | Outcome 1:Ensure sustainable development and management of the transport sector |  |  |  |  |  |  |  |
|  | Output 1.1 | Good gravelled roads | Km of Blading & Shaping of poor gravel roads | 222 | 35 | 27.3 | 7.7 |  |
|  | Output 1.2 | Desilting of streams, lined and unlined drains | M3 of desilted streams, lined & unlined drains | 7500 | 7200 | 6900 | 300 |  |
|  | Output 1.3 | Pothole patching within the municipality carried out | M2 of patched potholes within the municipality | 400 | 270 | - | 270 |  |
|  | Output 1.4 | Road signs in Effia-Kwesimintsim installed | 40 No. Road signs | 50 | 10 | - | - |  |
|  | Output 1.5 | Road line marking in Effia-Kwesimintsim completed | 18km centre line markings | 1700 | 500 | - | - |  |
|  | Output 1.6 | Drains Constructed among Selected Roads | Kms of Drains Constructed | 2.8 | 1.2 | 1.0 | 0.2 |  |
|  | Output 1.7 | Pipe Culverts on Selected Roads Reconstructed | No of Pipe Culverts Constructed | 45 | 12 | 10 | 2 |  |
|  | Output 1.8 | Renewed operational permit to all unions and operators | Number of operational permit for all registered unions renewed | - | - | - | - |  |
|  | Output 1.9 | Developed on and off street parking sites | Vehicle Parking Sites Developed | 2 | 1 | - | - |  |
| Sub Programme Objective: Facilitate sustainable and resilient infrastructure development |  |  |  |  |  |  |  |  |
| Physical and Spatial Planning Development | Outcome 2: Promote sustainable, spatially integrated & orderly human settlements |  |  |  |  |  |  |  |
|  | Output 2.1 | Statutory Planning committee meeting convened | Number of meetings held with minutes available | 12 | 12 | 12 | 0 |  |
|  | Output 2.2 | Planning Schemes prepared | Number of planning schemes approved at the statutory Planning Committee | 1 | 2 | 2 | 0 |  |
|  | Output 2.3 | Street Address and Properties numbered | Number of Streets signs post mounted | 50 Poles 82 Named Plates | 60 Poles 120 Named Plates | 73 Poles 143 Named Plates | (13) Poles (23) Named Plates |  |
|  |  |  | Number of properties numbered | 18,711 | 1000 | 1003 | (3) |  |
| Sub-Programme Objective: Ensure sustainable financing of investment, operation and maintenance of water service |  |  |  |  |  |  |  |  |
| Public Works, Rural Housing and Water Management | Outcome 3: Ensure sustainable financing of investment, operation and maintenance of water service |  |  |  |  |  |  |  |
|  | Output 3.1 | Illumination of communities undertaken | Number of street lights maintained | 898 | 950 | 900 | 50 |  |
|  | Output 3.2 | Community Boreholes drilled | Number of boreholes drilled | 11 | 10 | 5 | 5 |  |
|  | Output 3.3 | Communities provided with potable water | Number of communities with potable water | 12 | 12 | 12 | - |  |
|  | Output 3.4 | Bungalows Rehabilitated | Number of rehabilitated bungalows | Nil | Nil | Nil | nil | The assembly has no bungalows |
|  | Output 3.5 | Selected Feeder Roads Maintained | Number of feeder roads Maintained |  |  |  |  |  |

| ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| National Objective: Increase investment to enhance Agric productive capacity |  |  |  |  |  |  |  |  |  |
| Programme Objective: Improve private sector productivity & competitiveness domestically & globally and preserve Ghanaian cultural heritage |  |  |  |  |  |  |  |  |  |
| Sub-Programme | Type of Indicator | Description of Indicator | Unit of Measure of Indicator |  | Baseline (2021) Actuals | 2022 |  |  | Remarks |
|  |  |  |  |  |  | Budget Year Target | Annual Actual | Variance |  |
| Sub Programme Objective: Strengthen process towards achieving food sovereignty |  |  |  |  |  |  |  |  |  |
| Agricultural Services and Management | Outcome 1: Promote livestock & poultry development for food security & income generation |  |  |  |  |  |  |  |  |
|  | Output 1.1 | Increased access to extension service delivery | Number of farmers with access to extension service delivery |  | 1,396 | 1,500 | 1,289 | 211 |  |
|  | Output 1.2 | Increased production of major food crops | Metric Tons (mt) Produced per hectare (Ha) Number (000) | 2.50 | 3.0 | 2.78 | 0.22 |  |  |
|  |  |  |  | 7.99 | 8.10 | 8.05 | 0.05 |  |  |
|  |  |  |  | - | - | - | - |  |  |
|  |  |  |  | 20.40 | 21.00 | 20.91 | 0.09 |  |  |
|  | Output 1.3 | Increased production of poultry, small ruminants and pigs | Number of livestock produced | 655 | 1,000 | 742 | 258 |  |  |
|  |  |  |  | 50,500 | 55,000 | 54,323 | 677 |  |  |
|  |  |  |  | 551 | 800 | 684 | 116 |  |  |
|  |  |  |  | 4,375 | 5,000 | 5,124 | 124 |  |  |
|  | Output 1.4 | Organisation of Farmers’ Day undertaken | Number of Farmers' Day celebration held |  | 1 | 1 | 1 | 0 |  |
|  | Output 1.5 | Strengthened of farmer-based organizations | Number of farmer- based organizations trained |  | 2 | 6 | 4 | 2 |  |
|  | Output 1.6 | Increased cash crops production under Planting for Export and Rural Development (PERD) | Number of seedlings nursed |  | 20,000 | 21,000 | 17,000 | 4,000 |  |
|  |  |  | Number of beneficiary farmers |  | 242 | 300 | 158 | 142 |  |
|  | Output 1.7 | Quality and quantity of livestock production increased annually | Number of disease resistant livestock breeds introduced. |  | 500 | 600 | 0 | 600 |  |
| Sub Programme Objective: Improve private sector productivity & competitiveness domestically & globally |  |  |  |  |  |  |  |  |  |
| Trade, Tourism and Industrial Development | Outcome 2: Improve private sector productivity & competitiveness domestically & globally and Preserve Ghanaian cultural heritage |  |  |  |  |  |  |  |  |
|  | Output 1.1 | MSMEs access to Business Development Services improved | Number of MSMEs business supported |  | 987 | 410 | 320 | 90 |  |
|  |  |  | Number of MSMEs provided with training in record keeping |  | 173 | 100 | 80 | 20 |  |
|  |  |  | Number of MSMEs trained in financial literacy program |  | 173 | 100 | 80 | 20 |  |
|  |  |  | Number of women provided with Business Development Services |  | 1478 | 500 | 450 | 50 |  |
|  |  |  | Number of enterprises with access to business development services |  | 1942 | 800 | 710 | 90 |  |
|  | Output 1.2 | Accessibility to formal credit for MSMEs facilitated | Numbers of MSMEs supported with formal credit |  | 3068 | 3000 | 2995 | 5 |  |
|  | Output 1.3 | Promotional campaign designed and implemented | Number of promotional activities organized |  | 395 | 2193 | 2000 | 193 |  |

| ENVIRONMENTAL MANAGEMENT |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| National Objective: Reduce vulnerability to climate-related events and disasters |  |  |  |  |  |  |  |  |
| Programme Objective: To improve the livelihood of the poor and vulnerable in rural communities through effective disaster management, social mobilization and income generation. |  |  |  |  |  |  |  |  |
| Sub-Programme | Type of Indicator | Description of Indicator | Unit of Measure of Indicator | Baseline (2021) Actuals | 2022 |  |  | Remarks |
|  |  |  |  |  | Budget Year Target | Annual Actual | Variance |  |
| Sub Programme Objective: To enhance the capacity of society to prevent and manage disasters |  |  |  |  |  |  |  |  |
| Disaster Prevention and Management | Outcome 1: To enhance the capacity of society to prevent and manage disasters |  |  |  |  |  |  |  |
|  | Output 1.1 | Disaster prevention campaigns embarked on | Number of communities where anti-bush fire campaigns has been carried-out | - | 5 | - | 5 |  |
|  |  |  | Number of disaster prevention clubs formed | - | 4 | - | 4 |  |
|  |  |  | Number of inspections to disaster prone areas | 638 | 68 | 273 | 2 |  |
|  | Output 1.2 | Capacity to manage and minimize disaster improved annually | Number of rapid response unit for disaster established | - | - | - | - |  |
|  |  |  | Number bush fire volunteers trained | - | - | - | - |  |

# PART D: KEY FINANCIAL PERFORMANCE BY PROGRAMME FOR THE PERIOD

| FINANCIAL |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S/N | BUDGET PROGRAMME/ SUB-PROGRAMME NAME | APPROVED BUDGET (2022) | TOTAL APPROVED BUDGET BY FUND SOURCE |  |  |  |  | BUDGET (All Funding Sources) Period……… | ACTUAL EXPENDITURE FOR THE Period…….. | ACTUAL PAYMENTS FOR THE Period………. | PROJECTIONS FOR NEXT Period………. |
|  |  |  | GOG | DACF-RFG | IGF | DP FUND | DACF |  |  |  |  |
| P1 | Management and Administration |  |  |  |  |  |  |  |  |  |  |
| SP1. | General Administration | 3,302,509.34 | 1,142,073.75 |  | 1,476,260 |  | 684,175.59 | 3,302,509.34 | 3,299,043 | 2,998,411 | 9,070,512.28 |
| SP2 | Finance and Audit | 631,762 | 312,762 |  | 289,000 |  | 30,000 | 631,762 | 459,974 | 399,550 | 610,068 |
| SP3 | Human Resource Mgt | 198,886 | 88,886 |  | 50,000 |  | 60,000 | 198,886 | 178,452 | 170,003 | 93,142 |
| SP4 | Planning, Budgeting, Monitoring, Evaluation & Statistics | 2,553,511.17 | 663,687 |  | 250,000 | 1,639,824.17 | 210,000 | 2,553,511.17 | 1,840,233 | 1,704,112 | 178,122 |
| P2 | Social Services Delivery |  |  |  |  |  |  |  |  |  |  |
| SP1P | Education, youth & sports& Library services | G11,015,166,015,166 |  | 2472222555555666247,161 | 851285,000 |  | 683,005 | 1,015,166 | 399399,457 | 399,457 - | 1,526,044 |
| SP2 | Public Health Services & Mgt | 1,556,096 |  | 425,000 | 85,000 |  | 1,046,096 | 1,556,096 | 589,475 | 564,214 | 1,040,453 |
| SP3 | Env’t Health & Sanitation Services | 5,703,751 | 606,308 | 553,153 | 254,290 | 3,100,000 | 1,190,000 | 5,703,751 | 1,648,684 | 1,124,794 | 5,177,017 |
| SP4 | Birth & Death Registration Services | 10,000 |  |  | 10,000 |  |  | 10,000 | 8,400 | 8,400 | 9,000 |

NB: Breakdown of DP funds (Secondary cities, UNICEF, EU, etc.)

| FINANCIAL |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S/N | BUDGET PROGRAMME/ SUB-PROGRAMME NAME | APPROVED BUDGET (2022) | TOTAL APPROVED BUDGET BY FUND SOURCE |  |  |  |  | BUDGET (All Funding Sources) Period……… | ACTUAL EXPENDITURE FOR THE Period…….. | ACTUAL PAYMENTS FOR THE Period………. | PROJECTIONS FOR NEXT Period………. |
|  |  |  | GOG | DACF-RFG | IGF | DP FUND | DACF |  |  |  |  |
| SP5. | Social Welfare & Community Dev’t | 1,135,462 | 347,722 |  | 65,000 | 30,000 | 692,740 | 1,135,462 | 840,731 | 704,452 | 1,110,489 |
| P3 | Infrastructure Delivery & Mgt |  |  |  |  |  |  |  |  |  |  |
| SP1 | Roads & Transport Services | 18,688,576.28 | 90,000 |  | 60,000 | 18,158,576.28 | 380,000 | 18,688,576.28 | 7,630,888.94 | 5,706,314 | 18,638,792 |
| SP2 | Physical & Spatial Planning Dev’t | 1,180,031 | 417,841 |  | 70,000 | 100,000 | 592,190 | 1,180,031 | 346,141 | 336,110 | 370,791 |
| SP3 | Public Works | 5,068,980 | 995,040 |  | 244,000 | 2,500,000 | 1,329,940 | 5,068,980 | 968,935 | 952,143 | 4,743,584 |
| P4 | Economic Development | G |  |  |  |  |  | - |  | - |  |
| SP1 | Agricultural Services & Mgt | 1,010,134 | 620,875 |  | 35,000 | 114,259 | 240,000 | 1,010,134 | 430,337 | 408,822 | 567,370 |
| SP2 | Trade, Tourism & Industrial Dev’t | 226,000 |  |  | 50,000 |  | 80,000 | 130,000 | 73,345 | 73,345 | 3,877,994 |
| P5 | Environmental Management |  |  |  |  |  |  |  |  |  |  |
| SP1 | Disaster Prevention & Management | 240,000 |  |  | 30,000 | 150,000 | 60,000 | 240,000 | 106,949 | 106,949 | 286,818 |
|  | TOTAL | 42,520,864.79 | 5,245,194.75 | 1,236,314 | 2,968,550 | 25,792,659.45 | 7,278,146.59 | 42,520,864.79 | 18,821,130.54 | 15,657,077 | 47,300,192.28 |

NB: Breakdown of DP funds (Secondary cities, UNICEF, EU, etc.)

# PART E: SUMMARY OF EXPENDITURE BY ECONOMIC CLASSIFICATION

| EXPENDITURE ITEM | APPROVED BUDGET (2022) | *AMOUNT FOR THE PERIOD | ACTUAL EXPENDITURE FOR THE Period DECEMBER, 2022 | ACTUAL PAYMENTS FOR THE Period DECEMBER, 2022 | PROJECTIONS FOR NEXT Period 2023 |
| --- | --- | --- | --- | --- | --- |
| Compensation of Employees | 5,484,897.12 | 5,484,897.12 | 5,300,614.74 | 5,288,859.74 | 5,794,935.75 |
| Goods and Services | 10,706,257.47 | 10,706,257.47 | 5,766,046.51 | 4,866,991.96 | 14,907,841.11 |
| Capital Expenditure | 26,329,710.20 | 26,329,710.20 | 7,754,469.29 | 5,501,255.64 | 26,597,419.42 |
| Total | 42,520,864.79 | 42,520,864.79 | 18,821,130.54 | 15,657,077.34 | 47,300,196.28 |

# PART F: MMDAs CASH POSITION

| ACCOUNTS | ACCOUNT BALANCES AS AT 31ST DECEMBER, 2022 |
| --- | --- |
| Sub CF |  |
| GoG | - |
| DACF-RFG | 651,253.23 |
| DACF | 149,041.97 |
| Donor (UNICEF) | 15,000.00 |
| MAG | - |
| IGF | 11,860.29 |
| Ghana Secondary Cities Support Project (UDG) | 567,024.85 |
| MPCF | 221,060.05 |
| MSHAP | 32,183.57 |
| PWD | 66,533.93 |
| Total Cash position | 1,713,957.89 |

**please provide all other accounts and its balances if not listed above in accordance with Section 30(3) of the PFM Act

# PART G (i): SUMMARY OF 2022 IGF PERFORMANCE BY REVENUE ITEMS FOR THE PERIOD

| REVENUE CATEGORIES | PROJECTIONS/ BUDGET | ACTUAL COLLECTION DECEMBER, 2022 | PAYMENT INTO ASSEMBLY ACCOUNT DECEMBER, 2022 | REMARKS |
| --- | --- | --- | --- | --- |
| Property Rate | 820,000.00 | 689,155.07 | 689,155.07 |  |
| Other Rates (Basic Rate) | 20,000.00 | 2,571.00 | 2,571.00 |  |
| Fees | 307,500.00 | 291,621.28 | 291,621.28 |  |
| Fines | 24,000.00 | 14,316.00 | 14,316.00 |  |
| Licenses | 795,000.00 | 786,183.75 | 786,183.75 |  |
| Land | 470,000.00 | 524,072.19 | 524,072.19 |  |
| Investment | 32,000.00 | 122,810.00 | 122,810.00 |  |
| Sub Total | 2,468,500.00 | 2,430,729.29 | 2,430,729.29 |  |
| Royalties (Stool Lands) | 500,000.00 | 553,370.00 | 553,370.00 |  |
| Total | 2,968,550.00 | 2,984,099.29 | 2,984,099.29 |  |

## (II): EXPENDITURES ON 2022 IGFS BY ECONOMIC CLASSIFICATION

| EXPENDITURE ITEM | APPROVED BUDGET | ACTUAL EXPENDITURE FOR THE PERIOD December, 2022 |
| --- | --- | --- |
| Compensation of Employees | 353,961.37 | 351,995.39 |
| Goods and Services | 2,132,288.63 | 1,884,317.18 |
| Capital Expenditure | 482,300.00 | 284,046.32 |
| TOTALS | 2.968,550.00 | 2,520.358.89 |

# PART H: STAFF ESTABLISHMENT BY GRADE (GOG ONLY)

| S/N | GRADE | No. at post as at 31st December 2021 | No. at post as at December, 2022 | Projections for 2023 | Projections for 2024 | Projections for 2025 |
| --- | --- | --- | --- | --- | --- | --- |
|  | Co-ordinating Director | 1 | 1 | 1 | 1 | 1 |
|  | Deputy Director | 1 | 1 | 1 | 1 | 3 |
|  | Assistant Director I | - | 1 | 2 | 3 | 4 |
|  | Assistant Director IIA | 2 | 1 | 9 | 10 | 10 |
|  | Assistant Director IIB | 10 | 14 | 15 | 15 | 18 |
|  | Procurement Officer | 1 | 2 | 3 | 4 | 6 |
|  | Asst. Procurement Officer | 4 | 6 | 7 | 8 | 8 |
|  | Procurement Assistant | 2 | 3 | 5 | 6 | 7 |
|  | Principal Planning Officer | 1 | 1 | 1 | 1 | 1 |
|  | Snr. Planning Officer | 1 | 2 | - | 2 | 3 |
|  | Asst. Planning Officer | 2 | 2 | 3 | 4 | 5 |
|  | Senior Budget Analyst | 1 | 1 | 1 | 2 | 2 |
|  | Budget Analyst | - | 1 | 1 | 4 | 6 |
|  | Asst. Budget Analyst | 5 | 8 | 11 | 12 | 13 |
|  | Snr. Budget officer | 1 | - | - | 2 | 4 |
|  | Asst. Budget officer | - | - | 1 | 2 | 2 |
|  | Snr. System Analyst | 1 | 1 | 1 | 2 | 3 |
|  | Programmer | - | 1 | 1 | 3 | 5 |
|  | Asst. Programmer | 1 | 3 | 4 | 4 | 5 |
|  | Prin. Computer Operator | 1 | 1 | 1 | 4 | 5 |
|  | Prin. Data Entry Operator | 1 | 1 | 1 | 4 | 5 |
|  | Prin. Internal Auditor | 1 | 1 | 1 | 2 | 2 |
|  | Snr. Internal Auditor | 1 | 1 | 1 | 2 | 2 |
|  | Asst. Internal Auditor | 4 | 5 | 7 | 8 | 8 |
|  | Internal Auditor Trainee | 2 | 3 | 3 | 5 | 7 |
|  | Asst. Chief Executive Officer | - | 2 | 2 | 3 | 3 |
|  | Senior Executive Officer | 4 | 6 | 8 | 8 | 10 |
|  | Senior Private Secretary | - | 1 | 2 | 3 | 4 |
|  | Private Secretary | 1 | 2 | 2 | 3 | 3 |
|  | Steno. Secretary | 2 | 2 | 3 | 2 | 2 |
|  | Steno. Grade I | 4 | 2 | 2 | 2 | 2 |
|  | Steno. Grade II | 2 | 2 | 2 | 2 | 2 |
|  | Typist Grade II | 1 | 1 | 1 | 2 | 2 |
|  | Deputy Chief Metro Guard | 1 | 1 | 1 | 2 | 2 |
|  | Chief Inspector | 1 | 1 | 1 | 1 | 1 |
|  | Asst. Chief Tech. Instructor | 1 | 1 | 1 | 2 | 4 |
|  | Chief Conservancy Headman | 1 | 1 | 1 | 3 | 4 |
|  | Driver Grade I | 1 | 1 | 1 | 3 | 4 |
|  | Driver Grade II | 1 | 1 | 1 | 3 | 4 |
|  | Driver Grade III | - | 1 | 1 | 4 | 5 |
|  | Messenger/Scavenger | 1 | 1 | 1 | 3 | 4 |
|  | Assistant Security Officer | - | 3 | 3 | 5 | 10 |
|  | Prin. Revenue Superintendent | - | 1 | 1 | 3 | 5 |
|  | Snr. Revenue Superintendent | - | 1 | 1 | 3 | 4 |
|  | Revenue Superintendent | 1 | 1 | 1 | 4 | 5 |
|  | Statistician | - | 1 | 2 | 4 | 5 |
|  | Assistant Statistician | 4 | 5 | 6 | 7 | 8 |
|  | Snr. Env’tal Health Analyst | - | 1 | 1 | 2 | 4 |
|  | Asst. Env’tal Health Analyst | 2 | 3 | 3 | 4 | 7 |
|  | Chief Env’tal Health Asst. | 2 | 3 | 3 | 3 | 3 |
|  | Asst. Chief Env’tal Health Asst | 2 | 2 | 2 | 2 | 2 |
|  | Env’tal Health Officer GDI | 2 | 2 | 2 | 2 | 3 |
|  | Prin. Env’tal Health Asst. | 2 | 1 | 1 | 2 | 3 |
|  | Snr. Env’tal Health Officer | 2 | 2 | 2 | 3 | 4 |
|  | Env’tal Health Officer II | 2 | 2 | 2 | 4 | 5 |
|  | Snr. Env’tal Health Asst | 3 | 3 | 3 | 4 | 5 |
|  | Env’tal Health Asst | 3 | 4 | 4 | 5 | 6 |
|  | Human Resource Manager | - | 1 | 1 | 3 | 4 |
|  | Asst. Human Resource Manager | 3 | 2 | 2 | 3 | 6 |
|  | Director of Agric | 1 | 1 | 1 | 1 | 1 |
|  | Agric Officer | 2 | 2 | 2 | 3 | 4 |
|  | Asst. Agric Officer | 1 | 1 | 1 | 4 | 6 |
|  | Asst. Chief Tech. Officer | 2 | 2 | 2 | 3 | 5 |
|  | Prin. Tech. Officer | 1 | 1 | 1 | 2 | 4 |
|  | Snr. Tech Officer | 1 | 1 | 1 | 3 | 4 |
|  | Tech. Officer GD II | 2 | 2 | 2 | 3 | 4 |
|  | Production Officer | 1 | 1 | 1 | 4 | 5 |
|  | Prin. Physical Planning Officer | 1 | 1 | 1 | 2 | 2 |
|  | Asst. Physical Planning Officer | - | 1 | 1 | 5 | 7 |
|  | Prin. Tech. Officer | 2 | 2 | 2 | 3 | 4 |
|  | Snr. Technical Officer | 1 | 1 | 1 | 2 | 3 |
|  | Prin. Social Dev’t Officer | 1 | 1 | 1 | 2 | 2 |
|  | Snr. Social Dev’t Officer | 4 | 4 | 4 | 5 | 6 |
|  | Asst. Social Dev’t Officer | 5 | 6 | 7 | 8 | 9 |
|  | Principal Quantity Surveyor | 1 | 1 | 1 | 2 | 2 |
|  | Engineer | 1 | 4 | 4 | 6 | 7 |
|  | Architect | - | 1 | 1 | 3 | 4 |
|  | Asst. Engineer | 5 | 2 | 2 | 3 | 4 |
|  | Asst. Architect | 1 | - | - | 3 | 4 |
|  | Asst. Quantity Surveyor | 1 | 1 | 1 | 3 | 4 |
|  | Prin. Tech. Engineer | 1 | 1 | 1 | 1 | 2 |
|  | Tech. Engineer | 4 | 3 | 6 | 7 | 8 |
|  | Snr. Quantity Surveyor | 1 | 1 | 1 | 2 | 2 |
|  | Asst. Engineer | 1 | 1 | 2 | 3 | 3 |
|  | Asst. Quantity Surveyor | 1 | 1 | 1 | 2 | 4 |
| TOTAL |  | 113 | 177 | 209 | 296 | 357 |

# PART I: IGF STAFF BY NON-ESTABLISHED POST

| S/N | GRADE | No. at post as at 31st December 2021 | No. at post as at ……. 2022 | Projections for 2023 | Projections for 2024 | Projections for 2025 |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Presiding Member | 1 | 1 | 1 | 1 | 1 |
| 2 | Public Relations Officer | 1 | 1 | 1 | 2 | 2 |
| 3 | Revenue Collectors | 2 | 2 | 2 | 4 | 8 |
| 4 | Drivers | 4 | 3 | 3 | 5 | 6 |
| 5 | Constable (Guards) | 9 | 9 | 19 | 24 | 28 |
| 6 | Security | 13 | 13 | 13 | 20 | 20 |
| 7 | Sanitary Laborers | 8 | 8 | 8 | 12 | 14 |
| 8 | Cleaners | 14 | 14 | 14 | 18 | 18 |
| 9 | Sports Co-ordinator | 1 | 1 | 1 | 1 | 1 |
|  | TOTAL | 53 | 52 | 62 | 67 | 78 |

# PART J: ACTIONS TAKEN TO IMPLEMENT THE RECOMMENDATIONS OF PARLIAMENT IN RESPECT OF THE MOST RECENT REPORT OF THE AUDITOR-GENERAL IN ACCORDANCE WITH SECTION 27(4)(d) OF PFM Act

| S/N | RECOMMENDATIONS BY PARLIAMENT | ACTIONS TAKEN | REMARKS |
| --- | --- | --- | --- |
|  | 2019 Auditor General report (IGF) |  |  |
| 1 | Fictitious VAT Invoices GHS 969.68 PAC recommended that, all suppliers with fictitious VAT should be suspended and blacklisted from doing business with the Assembly | The Assembly has now suspended all the suppliers involved as per attached letter | Action taken |
|  | 2019 Auditor General report DACF |  |  |
| 2 | Fictitious VAT Invoices GHS 4,382.14 PAC recommended that, all suppliers with fictitious VAT should be suspended and blacklisted from doing business with the Assembly | The Assembly has now suspended all the suppliers involved as per attached letter | Action taken |

# PART K: DETAILS OF ON-GOING PROJECTS

| S/N | Name of Project and Location (a) | Contract Sum (b) | Variations in Contract sum | Total Revised Contract Sum (c) | Actual Payments to date | Balance | Last Payment made |  | Amount Budgeted for 2022 | Amount programmed for 2023 | Amount programmed for 2024 | ***Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Date | Amount |  |  |  |  |
| 1 | CONSTRUCTION OF 6-UINT CLASSROOM BLOCK WITH ANCILLARY FACILITIES AND 6-SEATER WATER CLOSET TOILET BLOCK WITH WATER TANK SUPPORT FOR MPATADO M/A BASIC SCHOOL | 814,956.89 | 0.00 | 814,956.89 | - | 814,956.89 | - | 0.00 | 820,000.00 |  |  | ON-GOING 10% COMPLETED (GETFUND) |
| 2 | CONSTRUCTION OF 2-UINT KINDERGARTEN CLASSROOM BLOCK WITH ANCILLARY FACILITIES FOR MPATADO M/A BASIC SCHOOL | 388,816.78 | 0.00 | 388,816.78 | - | 388,816.78 | - | 0.00 | 400,000.00 |  |  | SURFACE FINISHING WORKS ON-GOING 75% COMPLETED (GETFUND) |
| 3 | CONSTRUCTION OF 2-UINT KINDERGARTEN CLASSROOM BLOCK WITH ANCILLARY FACILITIES | 389,146.78 | 0.00 | 389,146.78 | - | 389,146.78 |  | 0.00 | 400,000.00 |  |  | BLOCK WORS ON-GOING 40% COMPLETED (GETFUND) |
| 4 | CONSTRUCTION OF 2-UINT KINDERGARTEN CLASSROOM BLOCK WITH ANCILLARY FACILITIES FOR APREMDO CATHOLIC SCHOOL | 535,260.44 | 0.00 | 535,260.44 | 0.00 | 535,260.44 | - | 0.00 |  |  |  | SURFACE FINISHING WORKSON-GOING 68% COMPLETED (GETFUND) |
| 5 | CONSTRUCTION OF 6-UINT CLASSROOM BLOCK WITH ANCILLARY FACILITIES AND 6-SEATER WATER CLOSET TOILET BLOCK WITH WATER TANK SUPPORT FOR ANAJI M/A BASIC SCHOOL | 1,094,833.85 | 0.00 | 1,094,833.85 | - | 1,094,833.85 | - | 0.00 |  |  |  | JOINERY WORKS ON-GOING 82% COMPLETED (GETFUND) |
| 6 | CONSTRUCTION OF PROPOSED TWO (2) STOREY HEALTH CENTRE (PHASE II) | 392,728.88 | 0.00 | 392,728.88 | 125,880.30 | 266,848.58 | 27TH OCT., 2020 | 69,991.65 |  |  |  | ROOFING COMPLETED 60% COMPLETED (MP’S NHIS/MPCF) |
| 7 | CONTINUATION AND COMPLETION OF COMMUNITY BASED HEALTH PLANNING AND SERVICE (CHPS) COMPOUND INCLUDING ACCOMMODATION, FURNISHING, MECHANIZED BOREHOLE, FENCE WALL AND GROUND WORKS AT APREMDO | 715,259.16 | 0.00 | 715,259.16 | 615,038.61 | 100,220.55 | 5TH APRIL, 2023 | 99,162.42 | 715,259.16 | 615,038.61 |  | HANDED OVER PRACTICALLY 100% COMPLETED (DACF) |
| 8 | CONSTRUCTION OF ONE (1) UNIT STAFF ACCOMMODATION FOR WHINDO HEALTH CENTRE (PHASE 1) AT WHINDO | 421,072.05 | 0.00 | 421,072.05 | 373,835.70 | 47,236.35 | 14TH APRIL, 2022 | 41,624.40 | 421,072.05 | 47,236.35 |  | HANDED OVER PRACTIALLY 100% COMPLETED (DACF-RFG) |
| 9 | CONSTRUCTION OF 2-BEDROOM FLAT SEMI-DETACHED STAFF ACCOMMODATION FOR ADIENTEM CHPS COMPOUND | 465,038.91 | 0.00 | 465,038.91 | 195,213.60 | 269,825.31 | 12TH JAN, 2023 | 88,879.50 | 425,000.00 | 358,704.80 |  | SURFACE FINISHING WORKSON-GOING 65% COMPLETED (DACF-RFG) |
| 10 | RENOVATION WORKS FOR PROVISION OF POLICE POST AT ABENBEBOM-APREMDO | 156,806.03 | 0.00 | 156,806.03 | 70,818.30 | 85,987.73 | 12TH JAN, 2023 | 70,818.30 | 156,806.03 | 156,806.03 |  | PAINTING WORKS ON-GOING 85% COMPLETED (DACF-RFG) |
| 11 | CONSTRUCTION OF 10NO. REFUSE COLLECTION POINTS AND FABRICATION OF 10NO. SKIP CONTAINERS-MUNICIPAL WIDE | 1,885,695.00 | 0.00 | 1,885,695.00 | 1,160,506.25 | 725,188.75 | 9TH SEPT., 2022 | 102,231.65 | 1,885,695.00 | 725,188.75 |  | ROOFING WORKS FOR FINAL 3 SITE ON-GOING 82% COMPLETED (GSCSP-UDGII) |
| 12 | CONSTRUCTION OF 10-SEATER WATER CLOSET TOILET AND 2-BAY URINAL BLOCK FOR WHINDO MARKET AT WHINDO | 245,755.54 | 0.00 | 245,755.54 | 203,999.00 | 41,756.54 | 29TH MARCH, 2023 | 29,131.65 | 245,755.54 | 70,888.19 |  | EXTERNAL WORKS ON-GOING 95% COMPLETED (DACF-RFG) |
| 13 | CONSTRUCTION OF 2NO.6-SEATER WATER CLOSET TOILET BLOCK FOR EAST TANOKROM MARKET AND GOOD SHEPHERD ANGLICAN SCHOOL. | 268,764.23 | 0.00 | 268,764.23 | 201,407.77 | 67,356.46 | 10TH AUG. 2022 | 88,751.90 | 268,764.23 | 67,356.46 |  | PRACTICALLY COMPLETED AWAITING HAND OVER 100% COMPLETED (DACF-RFG) |
| 14 | DRILLING OF 5 NO. MECHANIZED BOREHOLE AND WATER TANK SUPPORT WITH POLY TANK AT ANAJI, EFFIA NEW SITE, RACE COURSE& TADISCO DOWN | 256,147.50 | 0.00 | 256,147.50 | 237,749.50 | 18,398.00 | 19TH DEC. 2022 | 151,529.50 | 256,147.50 | 18,398.00 |  | PRACTICALLY COMPLETED AWAITING HAND OVER 100% COMPLETED (DACF-RFG) |
| 15 | PAVING OF ASSAKAE MARKET GROUNDS WITH A CONCRETE KERB. | 310,346.43 | 0.00 | 310,346.43 | 278,997.30 | 31,349.13 | 30TH JAN, 2023 | 278,997.30 | 310,346.43 | 310,346.43 |  | PRACTICALLY COMPLETED AWAITING HAND OVER 100% COMPLETED (DACF-RFG) |

***Remarks should include status of completion

# PART L: CONCLUSION

The details contained in this report inadvertently shows that the Assembly has a major gap to fill in order to bring much needed holistic development to Effia-Kwesimintsim Municipality. That, a concerted effort is required from every stakeholder if the Municipality wishes to experience development in every aspect of existence thereby, fulfilling its mission and realizing its goals

The table of content will have to be updated when report is completed to reflect the corresponding sections and page numbers